## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-4a-Better-Monkeys
Testing Team Name | fill in when doing cross-team testing
Sprint 2 stories
UI - search snacks using Search bar

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page.
Given that I am not on the Products page when I choose the Products page then I am taken to the Products page.
Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available.
Given that I am on the products page when there are products in the inventory then I see each product and short description.
Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart.
As a BUYER I want to SEARCH FOR SNACKS BY NAME so that I CAN FIND WHAT I WANT. | **Given** I ENTER A QUERY **when** A SNACK WITH A NAME CONTAINING THAT QUERY EXISTS **then** THE CATALOG UPDATES TO SHOW ALL SNACKS WITH A NAME CONTAINING THE QUERY. | Pass
| **Given** I ENTER A QUERY **when** A SNACK WITH A NAME CONTAINING THAT QUERY DOES NOT EXIST **then** THE CATALOG DISPLAYS NOTHING UNDER THE SEARCH BAR. | Pass
As a BUYER I want to VIEW A SNACK'S INFORMATION WITH A BUTTON TO ADD TO CART so that I CAN DECIDE IF I WANT TO BUY IT. | **Given** I AM IN THE CATALOG VIEW **when** CLICK ON A SNACK **then** I SEE A PAGE WITH THE SNACK NAME, PICTURE, DESCRIPTION, PRICE, AND A BUTTON TO ADD IT TO MY CART. | Pass
As a BUYER I want to SEE A SEARCH BAR AND A LIST OF CLICKABLE SNACKS so that I CAN SEARCH AND SELECT SNACKS I MIGHT BUY. | **Given** I AM NOT ALREADY IN THE CATALOG PAGE **when** I CLICK THE VIEW CATALOG BUTTON **then** I AM TAKEN TO THE CATALOG PAGE. | Pass
| **Given** I AM ALREADY IN THE CATALOG PAGE **when** I CLICK THE VIEW CATALOG BUTTON **then** I REMAIN ON THE CATALOG PAGE. | Pass
| **Given** I AM IN THE CATALOG PAGE **when** I SCROLL THROUGH THE PAGE **then** I SEE THE SEARCH BAR AT THE TOP FOLLOWED BY AN ARRAY OF SNACKS BELOW WITH NAMES, PICTURES AND PRICES. | Pass
As an OWNER I want to VIEW MY INVENTORY so that I CAN SEE WHAT IS AVAILABLE. | **Given** I AM LOGGED IN AS THE ADMIN AND NOT ALREADY IN THE INVENTORY PAGE **when** I CLICK THE VIEW INVENTORY BUTTON **then** I AM TAKEN TO THE INVENTORY PAGE. | Pass
| **Given** I AM LOGGED IN AS THE ADMIN AND AM ALREADY IN THE INVENTORY PAGE **when** I CLICK THE VIEW INVENTORY BUTTON **then** I STAY ON THE INVENTORY PAGE. | Pass
| **Given** I AM NOT LOGGED IN AS THE ADMIN **when** I AM ANYWHERE ON THE ESTORE **then** I CANNOT SEE THE VIEW INVENTORY BUTTON AND CANNOT ACCESS THE INVENTORY. | Fail | LL 11/1/2020 as a non member in the website I can still see the inventory button and access it
| **Given** I AM IN THE INVENTORY PAGE **when** I SCROLL THROUGH THE PAGE **then** I SEE A LIST OF SNACKS EACH WITH A NAME, PRICE, AND STOCK, WITH + AND - BUTTONS AND AN X BUTTON. THERE IS A TEXT BOX WITH AN ADD BUTTON AT THE BOTTOM OF THE PAGE. | Pass
As a BUYER I want to SEE A BUTTON TO SIGN UP FOR A MEMBERSHIP so that I CAN HAVE A MEMBERSHIP FOR THE WEBSITE. | **Given** A BUTTON TO SIGH UP FOR A MEMBERSHIP **when** I CLICK ON THAT BUTTON **then** I WANT TO BE TRANSFERRED TO ANOTHER PAGE WHERE I CAN CREATE AN ACCOUNT. | Pass
As a buyer I want to create an account with a username so that I can have can save my preferences. | **Given** the given username is unique **when** I try to sign up with a username **then** an account with the given information is created and the user is directed to the login screen. | Fail | LL 11/1/2020 Cannot register a memberiship/username with the website
| **Given** a username already exists **when** I try to sign up with the same username **then** I am told an account with the given username already exists and account creation fails. | Fail | LL 11/1/2020 Cannot register any username so cannot check if there are duplicates
As a USER I want to SEE A PAGE WHERE I CAN PUT MY LOGIN INFORMATION so that I HAVE ACCESS TO MY PROFILE WITHIN THE STORE. | **Given** A LOGIN BUTTON **when** I CLICK ON THAT BUTTON **then** I EXPECT TO BE TRANSFERRED TO A DIFFERENT PAGE WHERE I CAN LOG IN TO MY ACCOUNT. | Pass
As a buyer I want to log in to my existing account so I can shop with my saved shopping cart and preferences. | **Given** I have an account **when** I enter my username **then** I have the ability to access a shopping cart and purchase products | Fail | LL 11/1/2020 Cannot register a memberiship/username with the website
| **Given** I don't have an account **when** I enter a username **then** I am told the given information is invalid and I can only browse the Estore | Fail | LL 11/1/2020 Cannot register a memberiship/username with the website, and is still allowed to access features that are only reserved for members and the owner.
As an owner I want to log in as an admin so that I can manage the inventory. | **Given** I login with the owner's username **when** I enter a username **then** I enter the Estore as an admin. | Fail | LL 11/1/2020 Cannot register a memberiship/username with the website, and therefore cannot log in as the admin
As a user I want to log out of my account so that my information is not vulnerable when I leave. | **Given** I AM LOGGED IN **when** I CLICK THE LOG OUT BUTTON **then** I LOG OUT AND AM DIRECTED TO THE LOGIN SCREEN |  |  | Pass
| **Given** I AM LOGGED OUT **when** I AM VIEWING ANY PAGE ON THE ESTORE **then** THERE IS NO LOG OUT BUTTON |  |  | Pass
As a BUYER I want to VIEW THE CONTENTS OF MY CART so that I CAN DECIDE WHAT I WANT TO CHECK OUT. | **Given** I AM LOGGED OUT **when** I ENTER THE SHOPPING CART PAGE **then** I SEE A MESSAGE TO LOG IN TO ACCESS THE CART. |  |  | Pass
| **Given** I AM LOGGED IN AND ADDED NOTHING TO MY CART **when** I ENTER THE SHOPPING CART PAGE **then** I SEE A MESSAGE THAT MY CART IS EMPTY. |  |  | Pass
| **Given** I AM LOGGED IN AND HAVE ITEMS IN MY CART **when** I ENTER THE SHOPPING CART PAGE **then** I SEE THE LIST OF SNACKS IN MY CART, EACH WITH A PRICE, QUANTITY, + AND - BUTTONS, AND AN X BUTTON. THE TOTAL, AND CHECK OUT BUTTON ARE AT THE BOTTOM. |  |  | Pass
As a CUSTOMER I want to SEE SNACK RATINGS so that I CAN SEE EACH SNACK RATINGS CONSISTING OF COMMENTS AND STAR RATINGS. | **Given** A SNACK **when** I SEE THE SNACK IN INVENTORY **then** THE OVERALL RATING SHOULD BE UPDATED |  |  | Fail | Not implemented
As a CUSTOMER I want to PLACE SNACK RATINGS so that EACH SNACK HAS ITS OWN RATINGS CONSISTING OF COMMENTS AND STAR RATINGS. | **Given** A SNACK **when** I CLICK ON 1 OF THE 5 STARS **then** THE OVERALL RATING SHOULD BE UPDATED |  |  | Fail | Not implemented
As a BUYER I want to CHANGE THE QUANTITY OF SNACKS I WANT TO BUY so that I CAN ALTER THE AMOUNT OF SNACKS I WANT TO BUY IN MY SHOPPING CART. | **Given** a product with a plus or minus button on a snack in the shopping cart **when** I click on either plus or minus **then** the quantity of the snack decreases or increases in the shopping cart. |  |  | Pass
| **Given** a snack in the cart has a quantity of 1 **when** I click minus **then** the snack gets deleted. |  |  | Pass
As a BUYER I want to CHECK OUT PRODUCTS so that I CAN FINALIZE MY ORDERS AND RECEIVE MY PRODUCT. | **Given** I AM ON THE VIEW CART PAGE WITH PRODUCTS IN MY CART **when** I CLICK THE CHECK OUT BUTTON **then** SEE A MESSAGE THAT MY ORDER WAS SUCCESSFUL. |  |  | Pass
| **Given** I AM VIEWING THE INVENTORY AS THE OWNER **when** A BUYER HAS CHECKED OUT **then** I SEE THE QUANITITY OF THE ITEMS THEY BOUGHT GO DOWN. |  |  | Pass
As a BUYER I want to ADD A SNACK TO MY CART so that I CAN POTENTIALLY BUY IT. | **Given** I am in a snack's page, logged in, and the product is not already in my shopping cart, **when** I click a button to add the product to my cart **then** my shopping cart should have item included. |  |  | Pass
| **Given** I am in a snack's page but not logged in, **when** I click a button to add the product to my cart **then** I get a message that the I must log into an account before adding items to my cart. |  |  | Pass